## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Week 1 | Week 1 | US-001 | Requirement discussion, system analysis, feature list finalization | MUST HAVE | Mentors | Anisha G | Completed
Week 1 | Week 1 | US-002 | Setup backend (Spring Boot + MySQL), DB creation | MUST HAVE | Spring Boot, MySQL | Anisha G | Completed
Week 2 | Week 2 | US-003 | Implement Create Account API with validations | MUST HAVE | Backend | Anisha G | Completed
Week 2 | Week 2 | US-004 | Implement Login + Email OTP authentication | MUST HAVE | JavaMail API | Anisha G | Completed
Week 3 | Week 3 | US-005 | React Login & Create Account UI integration | MUST HAVE | React | Anisha G | Completed
Week 3 | Week 3 | US-006 | Implement Dashboard & account overview | MUST HAVE | React + Backend | Anisha G | Completed
Week 4 | Week 4 | US-007 | Deposit & Withdraw functionality with screens | MUST HAVE | DB Transactions | Anisha G | Completed
Week 4 | Week 4 | US-008 | Transfer money between accounts | MUST HAVE | DB, Backend | Anisha G | Completed
Week 5 | Week 5 | US-009 | Mini statement + full transaction history | SHOULD HAVE | SQL | Anisha G | Completed
Week 5 | Week 5 | US-010 | Profile management (update email & phone) | SHOULD HAVE | DB + UI | Anisha G | Completed
Week 6 | Week 6 | US-011 | Admin login & dashboard | MUST HAVE | Backend | Anisha G | Completed
Week 6 | Week 6 | US-012 | Admin: view users, freeze & unfreeze accounts | MUST HAVE | SQL | Anisha G | Completed
Week 7 | Week 7 | US-013 | Delete account (PIN verification) | SHOULD HAVE | Backend | Anisha G | Completed
Week 7 | Week 7 | US-014 | Loan module (Apply, Status, EMI view) | COULD HAVE | DB | Anisha G | Completed
Week 8 | Week 8 | US-015 | Notice Board (overdue dates, admin reminders) | MUST HAVE | Backend + React | Anisha G | Completed
Week 8 | Week 8 | US-016 | UI enhancement & testing + report preparation | MUST HAVE | Browser Testing, Postman | Anisha G | In Progress

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7