## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Week 1 | Week 1 | US-001 | Requirement discussion, system analysis, feature list finalization | MUST HAVE | Mentors | Manaswitha K | Completed
Week 1 | Week 1 | US-002 | Setup backend (Spring Boot + MySQL), DB creation | MUST HAVE | Spring Boot, MySQL | Manaswitha K | Completed
Week 2 | Week 2 | US-003 | Implement Create Account API with validations | MUST HAVE | Backend | Manaswitha K | Completed
Week 2 | Week 2 | US-004 | Implement Login + Email OTP authentication | MUST HAVE | JavaMail API | Manaswitha K | Completed
Week 3 | Week 3 | US-005 | React Login & Create Account UI integration | MUST HAVE | React | Manaswitha K | Completed
Week 3 | Week 3 | US-006 | Implement Dashboard & account overview | MUST HAVE | React + Backend | Manaswitha K | Completed
Week 4 | Week 4 | US-007 | Deposit & Withdraw functionality with screens | MUST HAVE | DB Transactions | Manaswitha K | Completed
Week 4 | Week 4 | US-008 | Transfer money between accounts | MUST HAVE | DB, Backend | Manaswitha K | Completed
Week 5 | Week 5 | US-009 | Mini statement + full transaction history | SHOULD HAVE | SQL | Manaswitha K | Completed
Week 5 | Week 5 | US-010 | Profile management (update email & phone) | SHOULD HAVE | DB + UI | Manaswitha K | Completed
Week 6 | Week 6 | US-011 | Admin login & dashboard | MUST HAVE | Backend | Manaswitha K | Completed
Week 6 | Week 6 | US-012 | Admin: view users, freeze & unfreeze accounts | MUST HAVE | SQL | Manaswitha K | Completed
Week 7 | Week 7 | US-013 | Delete account (PIN verification) | SHOULD HAVE | Backend | Manaswitha K | Completed
Week 7 | Week 7 | US-014 | Loan module (Apply, Status, EMI view) | COULD HAVE | DB | Manaswitha K | Completed
Week 8 | Week 8 | US-015 | Notice Board (overdue dates, admin reminders) | MUST HAVE | Backend + React | Manaswitha K | Completed
Week 8 | Week 8 | US-016 | UI enhancement & testing + report preparation | MUST HAVE | Browser Testing, Postman | Manaswitha K | In Progress
Note on F1: Mention the US ID(s) on which the user story depends. -Sumeet Kumar Barua08

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
Note on D2: 9/15/2016 or 15-Sep-2016 -Please enter the dates in either of these formats
Note on E2: 9/15/2016 or 15-Sep-2016 -Please enter the dates in either of these formats
Note on I3: This is the total task estimated in hours for all the user stories -Sumeet Kumar Barua08
Note on J3: Pending effort hours after completion of day 1 work -Sumeet Kumar Barua08
Note on K3: Pending effort hours after completion of day 2 work -Sumeet Kumar Barua08
Note on L3: Pending effort hours after completion of day 3 work -Sumeet Kumar Barua08
Note on M3: Pending effort hours after completion of day 4 work -Sumeet Kumar Barua08
Note on N3: Pending effort hours after completion of day 5 work -Sumeet Kumar Barua08
Note on O3: Pending effort hours after completion of day 6 work -Sumeet Kumar Barua08
Note on P3: Pending effort hours after completion of day 7 work -Sumeet Kumar Barua08
Note on Q3: Pending effort hours after completion of day 8 work -Sumeet Kumar Barua08
Note on R3: Pending effort hours after completion of day 9 work -Sumeet Kumar Barua08
Note on S3: Pending effort hours after completion of day 10 work -Sumeet Kumar Barua08
Note on T3: Pending effort hours after completion of day 11 work -Sumeet Kumar Barua08
Note on U3: Pending effort hours after completion of day 12 work -Sumeet Kumar Barua08
Note on V3: Pending effort hours after completion of day 13 work -Sumeet Kumar Barua08
Note on W3: Pending effort hours after completion of day 14 work -Sumeet Kumar Barua08

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7